## Sheet1
| Status | [5 empty] | Team 1: Elevator |  | Team 2: FSAE
| Complete | In Progress | Have not Started |  |  |  | Hayden |  | Zach
[7 empty] | Josh |  | Jesse
| Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7 | Task 8
Week 1 | Form Groups | Identify which group member are working on phase 1 to start and phase 3 (FSAE Component) | Download Tiger VNC and login to Elevator on school network and through VPN | Outline as a group the preliminary systems and how we will apply the elevator to FSAE | Health and Safety Quiz | Read Project Charter
Week 2 | Create Project Timeline | Get Altium Licesnse | Build Project Block Diagrams: System Communications Power Distribution Subsystems: eg, STM Periphirals Identify Electrical Subsystem | Create CANBUS Test plan | Tasks for debrief 2 | GUI Sketch
Week 3 | Task 1: Phase 1 - Technical; Task 4: Desiginging and Creating FSAE Electrical Schematics
Week 4 | Task 2: Phase 1 - Individual
Week 5 | Task 1: Phase 2 - Technical; Task 5: Tasks for Debrief 3
Week 6 | Task 4: Creating PCB and Placing Order for STM hats; Task 5: Tasks for debrief 4
Week 7 | Task 5: Tasks for Debrief 5
Week 8 - Week off
Week 9 | Task 5: Tasks for Debrief 6
Week 10 | Task 5: Tasks for Debrief 7
Week 11 | Task 2: Phase 2 - Individual
Week 12 | Task 1: Phase 3 - Technical; Task 2: Phase 3 - Individual; Task 5: Tasks for Debrief 8
Week 13
Week 14 | Task 2: Final Technical Presentation; Task 3: Final Code Submission